## Sheet1
| Project Part | Who worked on it | Status | Roadblocks | Before Spring Break | 3/26 - 4/8 | 4/9 - 4/15 | 4/16 - 4/22 | 4/23 - 4/29
Separate Project Modules: | ITCH Translator | Edward Liu | Complete |  | Able to successfully tranlate lobster file with a working testbench. Needs to be merged with Ethernet IN/OT
| Ethernet IN/OUT | Edward Liu | Complete | Fixed issues connecting HPS and FPGA logic. | Created tcp_sender.py. This program sends test TCP formated packets to FPGA | Created hps_tcp_reciever.py and verified packet communcation between laptop and FPGA. Also created tcp_packet_reciever.v but unable to program the board succesfully. | Fixed issues connecting HPS and FPGA logic. Ethernet Input complete. Ethernet Output complete. Need to merge with ITCH translator.
| Parser | Will Strong | Complete |  | Created and tested with a well developed testbench which will be useful during integration
| Execution Tracker (Python) | Bret Sell | Complete | Potential problems later matching the two trackers up together, cannot test until entire project completed. | Was complete & tested | Needed to be updated for OUCH format, should be completed now
| Execution Tracker (Verilog) | Bret Sell | Complete |  |  | Written & tested
| Order Books (Order price book) | Tyler Chen | Complete |  | Order Price Book Finished and Tested (2 stage pipeline). Full Level Book Finished Cache is 90% finished, waiting for Refill Engine to support the insert part | Refilling Engine with Epoch finsihed. Full FLB is tested in simulation. Designed an integration test for orderbook. Orderbook top module tested in both simulation and integration (7 stage pipeline). | Had some misunderstanding about bid/ask input and fixed it accordingly
| Trading Logic (Volatility) | Daniel Lei | Complete |  | New volatility module was created but not tested | New volatility module follows EWMA and is finished and tested | Added more tests and fully tested
| Trading Logic (Ln) | Will Strong | Complete |  |  | Created using a LUT and tested in simulation
| Trading Logic (Time) | Daniel Lei | Complete |  |  | Created but not tested | Tested and works in relation to market open duration
| Trading Logic (Division) | Daniel Lei | Complete |  |  | Created and tested in simulation
| Trading Logic Top Level | Daniel Lei, Will Strong | Complete | All submodules are put together and has testbench to verify mid-price, reservation based on inventory , spread based on inventory, and time of day behavior . Can be labelled complete since the core functionality works but want to improve coverage so a few additional test cases will be created to target edge cases. | Waiting for submodules to be completed | Full top level created and connected with submodules. Testbench created and tests core functionaltiy but want to test extra edge cases | Full level testbench complete follows, Avallenda Stoikov algorithm
| Risk Management | Bret Sell | Complete |  | Created & Tested
| Order Generator | Will Strong | Complete |  |  | Created and tested with another well developed testbench which can be used for integration
| Inventory Manager | Bret Sell, Daniel Lei | Complete |  | Created but not tested | Tested and simulated
| Market Simulation | Will Strong | Complete |  |  |  | Simulation of the market and our FPGA trading logic to work out ideal parameters for risk and liquidity
Integration so far: | After Trading logic testing (Risk manager -> order gen -> execution tracker -> inventory tracker) | Bret Sell | In Progress |  |  | ModelSim testing completed for this part, working on board test
| OrderBooks tested on board | Tyler Chen | Complete | 3/26 - 4/8: interacting with button
| Parser to Orderbook | Tyler Chen | Complete | 4/9 - 4/15: stored the messages inside a memory and parse through parser and output on the 8 segment display
Future Goals & Roadmap: | Project Part | Desired Completion |  | Comments
| Full implementation complete & tested on board | 2026-04-12 |  | Lot of integration this weekend, gives time to see if we need to find something other than ethernet if necessary
| Optimization team (timing, completity, multiple stocks) | 2026-04-16 |  | Optimization ideas: better profitability, multiple stocks, faster trades & clock timing, more quotes allowed in market,
| Demo team (software showing all stocks & info) | 2026-04-16 |  | Execution tracker in python should have most information on inventory, profits, and trades ready, just needs to make graphs and look pretty.
| Final Improvements, bug fixes, and internal demo | 2026-04-21
| Poster & Report Work | 2026-04-28